West of England Combined Authority Traffic Signal Enhancement Works

NPIF

RISK  MANAGEMENT STRATEGY

Release Status: Bid

Author: Gary Peacock, Highways and Traffic Deputy Group Manager

Date: 28 June 2017

# Contents

1	Contents	2

2	Introduction	3

2.1	Risk	3

2.2	Objectives of Risk Management	3

2.3	Scope of this Risk Management Strategy	4

2.4	Responsibility of this Risk Management Strategy	4

3	Risk Management Procedure	4

3.1	Identify Risks – Risk Categories	5

3.2	Risk Assessment	5

3.2.1	Risk Scales	5

3.2.2	Risk Actions	6

3.3	Plan	6

3.3.1	Objective of Risk Planning	6

3.3.2	Risk Response Categories	7

3.4	Implement	7

3.5	Communicate	8

4	Tools and Techniques	8

5	Records	8

6	Reporting	8

7	Timing of Risk Management Activities	9

8	Roles and Responsibilities	9

9	Proximity	10

9.1	Categorising Risk Proximity	10

9.2	Risk Proximity Actions	10

10	Early Warning Indicators	10

11	Risk Tolerance	11

12	Risk Budget	11

Appendix A – Risk Prompt List	12

Appendix B – Risk Register	13

# Introduction

## Risk

Risk is the chance or possibility of loss, damage, injury or failure to achieve objectives caused by an unwanted or uncertain action or event. Risk management is the planned and systematic approach to the identification, evaluation and control of risk. The objective of risk management is to secure the assets and reputation of the organisation and to ensure the continued financial and organisational well-being.

## Objectives of Risk Management

Good risk management is about identifying what might go wrong, what the consequences might be of something going wrong and finally, deciding what can be done to reduce the possibility of something going wrong. If it does go wrong, as some things inevitably will, making sure that the impact is kept to a minimum.

Risk management should ensure that an organisation makes cost effective use of a risk framework that has a series of well-defined steps. The aim is to support better decision making through a good understanding of risks and their likely impact.

Risk management should be a continuous and developing process which runs throughout the organisation’s strategy and the implementation of that strategy, methodically addressing all risks surrounding the council’s activities past, present and future.

The risk management objectives are to:

- Ensure that risk management is clearly and consistently integrated and evidenced in the culture of the organisation.

- Manage risk in accordance with best practice.

- Anticipate and respond to changing social, environmental and legislative requirements.

- Consider compliance with health and safety, insurance and legal requirements as a minimum standard.

- Prevent death, injury, damage and losses, and reduce the cost of risk.

- Inform policy and operational decisions by identifying risks and their likely impact.

- Raise awareness of the need for risk management by all those connected with the organisation’s delivery of service.

These objectives will be achieved by:

- Clearly defining the roles, responsibilities and reporting lines within the organisation for risk management.

- Including risk management issues when writing reports and considering decisions.

- Continuing to demonstrate the application of risk management principles in the activities of the organisation, its employees and member companies.

- Reinforcing the importance of effective risk management as part of the everyday work of employees and members.

- Maintaining a register of risks linked to the organisation’s business, corporate and operational objectives, also those risks linked to working in partnership.

- Maintaining documented procedures of the control of risk and provision of suitable information, training and supervision.

- Maintaining an appropriate system for recording health and safety incidents an identifying preventative measures against recurrence.

- Preparing contingency plans to secure business continuity where there is a potential for an event to have a major impact upon the organisation’s ability to function.

- Monitor arrangements continually and seek continuous improvement.

## Scope of this Risk Management Strategy

FMD Consultants Limited maintains a corporate risk management strategy which controls risks associated with the company as a whole, its relationship with its clients and the management of new and existing business relationships.

This Risk Management Strategy is a subset of the corporate Risk Management Strategy and relates specifically to procedures related to the development of software applications, provision of methodology documentation and the presentation of that information to the general public as a whole.

## Responsibility of this Risk Management Strategy

The responsibility for the creation, maintenance and periodic review of this Risk Management Strategy is held Paul Garrod, Highway Network Manager B&NES.

It will be reviewed on a monthly basis and changed ratified through peer-group review.

# Risk Management Procedure

The Risk Management Procedure encompasses 5 activities:

Communicate

## Identify Risks – Risk Categories

Involved parties detailed in Roles and Responsibilities, below, should concentrate on events that might affect the organisation’s achievement of its objectives. This should focus on areas which may impact costs, timescales, quality of deliverables, maintainability or usability of any products. Strategic risks linked to the Corporate Objectives and Operational risks linked to service and project plans need (as a minimum) to be identified and monitored. Techniques recommended to identify risks are:

Review Lessons - Review lessons learned logs for similar profile work streams to determine where uncertainties lay and see what threats and opportunities impacted them.

Risk Prompt List – Examine the Risk Prompt List (Appendix A – Risk Prompt List) in the context of the work stream to determine if any of the defined areas of risk may be applicable. This details known risk types which should be considered when determining the risk to the project and fall under the headings of:

- Economic Risks

- Environmental Risks

- Financial Risks

- Governmental Risks

- Legal Risks

- Operational Risks

- Perception Risks

- Personnel Risks

- Project Risks

- Security Risks

- Strategic/ Commercial Risks

- Structures & Policies Risks

- Technical/ Infrastructure Risks

Brainstorming – Utilise group brainstorming to identify prospective risks which may not be recognised by an individual. Utilise disparate groups for brainstorming to provide alternative views of risks, for example user groups, development groups, finance heads and project related personnel.

Project Schedules – Are any areas of the project falling behind schedule i.e. is the percentage of work package completed running to schedule. Have all approval target dates been met.

Project Finances – Is the project running to budget and within tolerance? Are there any exceptional costs which were not forecast?

Project Performance – Is the number of issues raised higher than expected or greater than has been experienced in earlier projects. Are there a high percentage of issues which are unresolved. Does it take longer to resolve issues than would normally be expected. Are problems being experienced with any of the projects product quality.

## Risk Assessment

### Risk Scales

Following the identification of risks, they will then be included in the risk register which will identify the risk owner and the steps being taken to mitigate the risk. Risks will be categorised against the potential impact to the business on a scale of 1 to 10, 1 being the lowest impact and 10 being the highest impact. Risks will also be categorised against the likelihood of the risk being encountered on a scale of 1 to 10, 1 being the lowest likelihood and 10 being the highest likelihood.

The Risk Impact and Risk Likelihood will then be multiplied to give a total risk score, 1 being the lowest and 100 being the highest possible risk.

A total risk score of:

- Below 30 will give a ‘green’ risk.

- Between 31 and 59  give an ‘amber’ risk

- Above 60 give a ‘red’ risk

### Risk Actions

| Risk Impact | Score | Frequency of Review |
| --- | --- | --- |
| No action necessary | < 10 | n/a |
| Monitor as necessary - ensure being properly managed | < 20 | Quarterly |
| Monitor as necessary - less important but still could have a serious effect on the provision of key services or duties | < 30 | Quarterly |
| Monitor as necessary- less important but still could have a serious effect on the provision of key services or duties | < 40 | Monthly |
| Monitor as necessary - less important but still could have a serious effect on the provision of key services or duties | < 50 | Monthly |
| Important risks - may potentially affect provision of key services or duties | < 60 | Weekly |
| Key risk- may potentially affect provision of key services or duties | > 60 | Immediate |
| Immediate action needed - serious threat to Provision and/or achievement of key services or duties | > 80 | Immediate |

## Plan

### Objective of Risk Planning

The primary objective of this step is to prepare management responses using Risk Response Categories for each of the identified threats and opportunities in order to reduce or remove the threat or to maximize the opportunity. This should leave the project prepared with an action plan should any risk materialise.

Concentration should be on ‘red’ risks as these have the greatest chance of arising and are likely to impact the project most severely. Consideration should be given to ‘amber’ risks and ‘green’ risks in order to:

- Keep the risk at as low a level as is practical

- Be prepared to respond to the risk should its severity level increase during the project

- Ensure that ‘green’ or ‘amber’ risks do not increase the chance of a ‘red’ risk being encountered

### Risk Response Categories

- Avoid – typically change an aspect of the project so the threat can no longer happen

- Reduce – Either reduce the chance of the threat occurring or reduce the impact of the threat should it occur

- Fallback – Build a fallback plan for actions which will reduce the threat should the risk occur

- Transfer – A third party takes on responsibility for some of the financial impact of the threat (via insurance or contractual agreement) to reduce the financial cost of the threat

- Accept – accept that the threat may be encountered, usually because it is either unavoidable or financially unviable to avoid the threat

- Share – work with third parties to share either the cost loss or gain associated with the threat

- Exploit – seize an opportunity to ensure the opportunity will happen and the beneficial outcome will be realised

- Enhance – take actions to improve the probability of an event occurring and to enhance the beneficial outcome should it occur

- Reject – a conscious decision not to exploit an opportunity as it is more economical to continue without responding

## Implement

The primary objective of this step is to ensure the planned risk responses are implemented, their effectiveness monitored and corrective action taken where responses do not provide effective solutions.

To ensure this is carried out efficiently, there will be a sole Risk Owner. This is a named individual who is responsible for the management, monitoring and control of all aspects of a particular risk.

There may be a Risk Actionee responsible for carrying out the required response action for a risk or set of risks. The Risk Actionee should perform under the direction of the Risk Owner.

The Risk Owner and Risk Actionee may be the same person.

A risk will be assigned to a single individual.

An individual may be responsible for more than one risk but consideration should be given to their workload and abilities to ensure any individual is not allocated more risks than they can practically manage.

## Communicate

Risks will be communicated outwards as part of:

- Checkpoint Reports - frequency defined in each Work Package, minimum of monthly

- Highlight Reports - defined by Project Board, minimum of monthly

- End Stage Reports

- End Project Reports

- Lessons Reports – at End Stage and End Project

Inwards communications of risks, in particular new perceived risks should to the Project Manager for assessment, ad-hoc and openly welcomed.

# Tools and Techniques

Project risk will be managed through electronic library store of completed Risk Register Forms with a hard-copy back-up of the forms maintained within the Project Office. Each Risk Register form will detail the status of a single risk and will have a unique, sequential risk identifier.

Access to Risk Register forms will be restricted to those defines in the roles and responsibilities, below and to the Risk Owner.

# Records

Appendix B – Risk Register details the format of the Risk Register and contains descriptions for each Risk Register field.

# Reporting

Individual risk overviews will be entered on the Risk Summary which will be readily available for authorised individuals and which will be circulated at Project Boards.

The Risk Summary will detail:

- Programme Name / Project Name

- Risk Identifier

- Summary of risk description

- Risk Category

- Current risk colour (green, amber, red)

- Current risk weighting

- Previous risk colour (green, amber, red)

- Date registered

- Risk Owner

Access to Risk Summary will be restricted to those defined in the roles and responsibilities (section 8) and to the Risk Owner.

# Timing of Risk Management Activities

The Risk Register will be created on approval of this Risk Management Strategy. It will be updated:

- On planning the next stage

- On authorizing a work package

- On any updates of the project plan

- Upon any updates of the Business Case

- On the production of any exception plan

- On review of any stage status

It will be closed when approval for project closure has been given by the Project Executive.

# Roles and Responsibilities

| Role | Responsibility |
| --- | --- |
| Corporate Management | Provide the corporate risk management policy and risk management guide. |
| Executive | Be accountable for all aspects of risk management and ensure an approved project Risk Management Strategy exists. Ensure risks associated with the Business Case are identified, assessed and controlled. Escalate risks to corporate management as necessary. |
| Senior User | Ensure all risks to the users are identified, assessed and controlled. |
| Senior Supplier | Ensure risks relating to the supplier aspects are assessed and controlled. |
| Project Manager | Create the Risk Management Strategy. Create and maintain the Risk Register. Ensure all project risks are being identified, assessed and controlled throughout the project lifecycle. |
| Team Manager | Participate in the identification, assessment and control of risks. |
| Project Assurance | Review risk management practices to ensure they are performed in line with the projects Risk Management Strategy. |
| Project Support | Assist the Project Manager in maintaining the project’s Risk Register and Risk Summary. |

# Proximity

## Categorising Risk Proximity

Risk events will be categorised as:

- Imminent – likely to be encountered immediately, typically within one week or less

- Within the stage – likely to be encountered during the current stage of the project

- Next stage – likely to be encountered during the next planned stage of the project

- Within the project – likely to be encountered before the project is closed

- Beyond the project – likely to be encountered after project closure

## Risk Proximity Actions

Imminent risks should be noted separately within reporting to highlight the risk to project members to ensure it is being monitored adequately.

On completion of a stage, ‘within the stage’ risks should be assessed to determine if they were encountered. If they were not encountered their relevance to the next planned stage should be determined and their proximity classification modified accordingly.

On completion of a stage, ‘next stage’ risks should be assessed to determine if they are still applicable to the next stage (i.e. the stage to be started) and, if appropriate, their proximity should be modified to ‘within the stage’.

‘within the project’ risks should be reviewed at stage end to determine if they fall into the ‘next stage’ category (i.e. the stage after the stage to be started).

‘beyond the project’ risks should be reviewed at stage end to determine if they are still legitimate risks. If the project is at closure stage, these risks should be highlighted in the project closure documentation.

# Early Warning Indicators

There are several early warning indicators which should be monitored during the lift of the project:

- Forecast project spend / timescales exceeding approved tolerance – should the forecast total spend exceed the project budget plus allowed tolerance, it is clear there is a genuine risk of overspend (or non-completion) of the project. This should be regularly monitored by the project manager to ensure spend is within allowed limits

- Forecast stage spend / timescales exceeding approved tolerance – the implication is that the stage has either been incorrectly costed, incorrectly defined or has encountered unforeseen problems.

- Product quality not meeting quality requirements – have there been shortcuts in the production of products which detrimentally impact product quality. In particular, has spend to date fallen below the forecast spend to date or the products been delivered earlier than planned.

These should be regularly monitored by the Project Manager / Project Support to ensure each stage is performing according to planned cost, timescales and quality.

# Risk Tolerance

Risks are scored on a scale of 1 to 100, one hundred being the greatest risk. Risks with a score greater than 60 should be noted to corporate management for information. Risks should be escalated to corporate management immediately the risk score exceeds 80.

# Risk Budget

There is no specific risk budget. Project tolerance will be employed where necessary to minimise the impact of risks.

It should be noted that there may be some risks defined during the project which require a separate budget, e.g. insurance against risk encounter or insurance against financial implications of risks.

#### Appendix A – Risk Prompt List

Checklist of Common Risk Sources

| Personnel Risks |  | Governmental Risks |  |
| --- | --- | --- | --- |
|  | Illness |  | Permits |
|  | Conflict |  | Customs |
|  | Labour Problems |  | Environmental Standards |
|  | Skill Shortage |  | Patents |
|  | Motivation |  | Health & Safety |
|  | Commitment |  | Nuclear Regulations |
| Project Risks |  | Strategic/ Commercial Risks |  |
|  | Budget |  | Under-performance to specification |
|  | Scope/ Complexity |  | Management will under – perform |
|  | Vision |  | Insufficient Capital Revenues |
|  | Decision Process |  | Lack of availability of Capital Investment |
|  | Timescale |  |  |
|  | Commitment | Perception Risks |  |
|  | Politics |  | Racially/ethnically/gender offensive |
|  | Poor Estimating |  | Health Threatening |
| Security Risks |  | Financial Risks |  |
|  | Theft |  | Cash Flow |
|  | Espionage |  | Payments |
|  | Natural Disaster |  | Exchange Rates |
|  |  |  | Operational & Maintenance Costs |
| Operational Risks |  |  | Procurement Costs |
|  | Inadequate Business Continuity |  |  |
|  | Health & Safety Constraints | Economic Risks |  |
|  | Marketing/ Communications |  | Shortage of Working Capital |
|  | Manufacturing |  | Failure to meet projected revenue targets |
|  | Purchasing |  | Market Developments have adverse effects |
|  | Inadequate Design |  |  |
|  | Professional Negligence | Legal Risks |  |
|  | Human Error/ Incompetence |  | Scope Creep |
|  | Safety being compromised |  | Contract |
|  | Performance Failure |  | Personal Liability |
|  | Unclear Expectations |  | Penalty Clauses |
|  | Breaches in Security |  | New or Change legislation impacts activity |
|  |  |  | Unforeseen regulatory controls or licensing |
| Structures & Policies Risks |  |  | requirements |
|  | Business Structure |  |  |
|  | Business Planning Process | Technical/ Infrastructure Risks |  |
|  | Service Plan |  | Scalability |
|  | IT Plan |  | Integration |
|  | Recruitment Process |  | Security |
|  | Staff Development Process |  | Standards |
|  | Managerial & Accountability Structures |  | Compatibility |
|  | Change Management Procedure |  | Performance |
|  | Risk Management Procedure |  | Inadequate Design |
|  | Quality Management Procedure |  | Infrastructure Failure |
|  | Organisational Strategy |  | Increased decommissioning costs |
|  | IS Programme Plan |  | Residual Maintenance Problems |
|  | Contingency Management Procedure |  |  |
|  | Bureaucracy | Environmental Risks |  |
|  | Complaints Handling Procedure |  | Transport Problems |
|  |  |  | Building Facilities & Temperature |

#### Appendix B – Risk Register

| RISK REGISTER |  |  |  |  |  |  | Version: Bid |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Name: West of England Combined Authority Traffic Signal Enhancement Works |  |  |  |  |  |  | Project Name: Programme Level |  |  |  |  |  |
| Risk Identifier: 001 |  |  | Risk Description: Management will under perform |  |  |  |  |  |  |  | Risk Category: Project |  |
| Probability: |  |  |  | Impact: |  |  |  | Expected Value: |  |  | Proximity: Bid Approval |  |
| Pre-Response 5 | Post-Response 2 |  |  | Pre-Response 7 | Post-Response 5 |  |  | Pre-Response 35 |  | Post-Response 10 |  |  |
| Risk Response Category: - Reduce the chance of the threat occurring or reduce impact of threat should it occur |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Response: A Project Board will be set up, the makeup has been agreed, there will be Senior Management Staff from each Council and suppliers with key skills to provide direction and where required interventions. Each junction improvement scheme will be delivered by an experienced Engineer reporting direct to the Project Manager who will report monthly to the Board. Project Plans including cost plans and programmes will be agreed by the Board. Any actual variations or forecast variations will be reported to the Board and actions agreed. Any poor performing schemes will be actively managed to mitigate the impact on the overall programme. The scheme delivery will comply with the Councils Capital Delivery Project Management requirements. |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Registered: 26th June 2017 |  | Risk Author: Gary Peacock |  |  |  | Risk Owner: Richard Lewis Project Manager |  |  | Risk Actionee: Project Manager |  |  | Risk Status: Active |

| RISK REGISTER |  |  |  |  |  |  | Version: Bid |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Name: West of England Combined Authority Traffic Signal Enhancement Works |  |  |  |  |  |  | Project Name: Programme Level |  |  |  |  |  |
| Risk Identifier: 002 |  |  | Risk Description: Tender costs exceed forecast |  |  |  |  |  |  |  | Risk Category: Project |  |
| Probability: |  |  |  | Impact: |  |  |  | Expected Value: |  |  | Proximity: Procurement |  |
| Pre-Response 7 | Post-Response 2 |  |  | Pre-Response 6 | Post-Response 6 |  |  | Pre-Response 42 |  | Post-Response 12 |  |  |
| Risk Response Category: - Reduce the chance of the threat occurring or reduce impact of threat should it occur |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Response: Works will be delivered through termed contracts, using existing schedule of rates. This provides greater cost certainty. The Council have an existing contract with Dyniq for the traffic signals and civils will be delivered by the Councils Termed Civils contractors. |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Registered: 26th June 2017 |  | Risk Author: Gary Peacock |  |  |  | Risk Owner: Richard Lewis Project Manager |  |  | Risk Actionee: Project Manager |  |  | Risk Status: Active |

| RISK REGISTER |  |  |  |  |  |  | Version: Bid |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Name: West of England Combined Authority Traffic Signal Enhancement Works |  |  |  |  |  |  | Project Name: Programme Level |  |  |  |  |  |
| Risk Identifier: 003 |  |  | Risk Description: Poor Contractor Performance |  |  |  |  |  |  |  | Risk Category: Project |  |
| Probability: |  |  |  | Impact: |  |  |  | Expected Value: |  |  | Proximity: Construction |  |
| Pre-Response 5 | Post-Response 2 |  |  | Pre-Response 8 | Post-Response 5 |  |  | Pre-Response 40 |  | Post-Response 10 |  |  |
| Risk Response Category: - Reduce the chance of the threat occurring or reduce impact of threat should it occur |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Response: As termed contractors will be used, a meeting has been held with Dyniq to assess their involvement and provide early feedback from the contractor. Dyniq have confirmed they have adequate capacity and have added the potential works to their forward programme for 2018. Continued early contractor involvement will continue to allow the works to be actively developed with the contractors. The contractor will join the Board as a Senior Supplier which combined with the early contractor involvement should assist with good performance and addressing any poor performance issues. |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Registered: 26th June 2017 |  | Risk Author: Gary Peacock |  |  |  | Risk Owner: Richard Lewis Project Manager |  |  | Risk Actionee: Project Manager |  |  | Risk Status: Active |

| RISK REGISTER |  |  |  |  |  |  | Version: Bid |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Name: West of England Combined Authority Traffic Signal Enhancement Works |  |  |  |  |  |  | Project Name: Programme Level |  |  |  |  |  |
| Risk Identifier: 004 |  |  | Risk Description: Cost over run |  |  |  |  |  |  |  | Risk Category: Project |  |
| Probability: |  |  |  | Impact: |  |  |  | Expected Value: |  |  | Proximity: Delivery |  |
| Pre-Response 5 | Post-Response 2 |  |  | Pre-Response 7 | Post-Response 5 |  |  | Pre-Response 35 |  | Post-Response 10 |  |  |
| Risk Response Category: - Reduce the chance of the threat occurring or reduce impact of threat should it occur |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Response: The Project Manager will report monthly to the Board to ensure cost are actively forecasted and managed throughout life of the programme. Potential cost variations will be identified at an early stage and monitored by the Board, scheme mitigations will be assessed, followed by programme mitigation. Any variations will be subject to a Change Control process. Potential cost increases outside Programme variance will be managed by the Councils through their internal financial controls who will confirm back to the Board their decisions on any additional funding. |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Registered: 26th June 2017 |  | Risk Author: Gary Peacock |  |  |  | Risk Owner: Richard Lewis Project Manager |  |  | Risk Actionee: Project Manager |  |  | Risk Status: Active |

| RISK REGISTER |  |  |  |  |  |  | Version: Bid |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Name: West of England Combined Authority Traffic Signal Enhancement Works |  |  |  |  |  |  | Project Name: Programme Level |  |  |  |  |  |
| Risk Identifier: 005 |  |  | Risk Description: Scope Creep |  |  |  |  |  |  |  | Risk Category: Project |  |
| Probability: |  |  |  | Impact: |  |  |  | Expected Value: |  |  | Proximity: Procurement |  |
| Pre-Response 5 | Post-Response 2 |  |  | Pre-Response 7 | Post-Response 5 |  |  | Pre-Response 35 |  | Post-Response 10 |  |  |
| Risk Response Category: - Reduce the chance of the threat occurring or reduce impact of threat should it occur |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Response: Each junction improvement will have a defined scope agreed by the Board. Any change will be subject to the Board approval and Change Control process. This will enable risks or opportunities relating to time, cost and quality to be quantified and assessed by the Board before any change decision. |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Registered: 26th June 2017 |  | Risk Author: Gary Peacock |  |  |  | Risk Owner: Richard Lewis Project Manager |  |  | Risk Actionee: Project Manager |  |  | Risk Status: Active |

| RISK REGISTER |  |  |  |  |  |  | Version: Bid |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Name: West of England Combined Authority Traffic Signal Enhancement Works |  |  |  |  |  |  | Project Name: Programme Level |  |  |  |  |  |
| Risk Identifier: 006 |  |  | Risk Description: Statutory Undertaker Works lead to delays |  |  |  |  |  |  |  | Risk Category: Project |  |
| Probability: |  |  |  | Impact: |  |  |  | Expected Value: |  |  | Proximity: Delivery |  |
| Pre-Response 5 | Post-Response 2 |  |  | Pre-Response 7 | Post-Response 6 |  |  | Pre-Response 35 |  | Post-Response 12 |  |  |
| Risk Response Category: - Reduce the chance of the threat occurring or reduce impact of threat should it occur |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Response: The Councils will continue to work closely to co-ordinate utility works through their Street Works Team. The potential works will be added to co-ordination schedules to allow the utilities companies to identify opportunities for joined working. Any diversionary works required for the schemes will be identified at an early stage of design process and delivered through the C2 to C4 process. |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Registered: 26th June 2017 |  | Risk Author: Gary Peacock |  |  |  | Risk Owner: Richard Lewis Project Manager |  |  | Risk Actionee: Project Manager |  |  | Risk Status: Active |

| RISK REGISTER |  |  |  |  |  |  | Version: Bid |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Name: West of England Combined Authority Traffic Signal Enhancement Works |  |  |  |  |  |  | Project Name: Programme Level |  |  |  |  |  |
| Risk Identifier: 007 |  |  | Risk Description: Delays due to other works on the Highway Network preventing scheme starting |  |  |  |  |  |  |  | Risk Category: Project |  |
| Probability: |  |  |  | Impact: |  |  |  | Expected Value: |  |  | Proximity: Delivery |  |
| Pre-Response 5 | Post-Response 2 |  |  | Pre-Response 5 | Post-Response 5 |  |  | Pre-Response 25 |  | Post-Response 10 |  |  |
| Risk Response Category: - Reduce the chance of the threat occurring or reduce impact of threat should it occur |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Response: The schemes will be added to the street works register and road space booked at the earliest opportunity. This will reserve the road space and allow co-ordination of works on the network. |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Registered: 26th June 2017 |  | Risk Author: Gary Peacock |  |  |  | Risk Owner: Richard Lewis Project Manager |  |  | Risk Actionee: Project Manager |  |  | Risk Status: Active |
| RISK REGISTER |  |  |  |  |  |  | Version: Bid |  |  |  |  |  |
| Programme Name: West of England Combined Authority Traffic Signal Enhancement Works |  |  |  |  |  |  | Project Name: Programme Level |  |  |  |  |  |
| Risk Identifier: 008 |  |  | Risk Description: Delays in obtaining approvals |  |  |  |  |  |  |  | Risk Category: Project |  |
| Probability: |  |  |  | Impact: |  |  |  | Expected Value: |  |  | Proximity: Delivery |  |
| Pre-Response 5 | Post-Response 3 |  |  | Pre-Response 4 | Post-Response 4 |  |  | Pre-Response 20 |  | Post-Response 12 |  |  |
| Risk Response Category: - Reduce the chance of the threat occurring or reduce impact of threat should it occur |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Response: Works are within the Public Highway and no third party land or planning permission are required. A milestone chart identifying the programme approvals dates will be produced and monitored. Each junction scheme will provide a milestone approval chart as part of their programme. |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Registered: 26th June 2017 |  | Risk Author: Gary Peacock |  |  |  | Risk Owner: Richard Lewis Project Manager |  |  | Risk Actionee: Project Manager |  |  | Risk Status: Active |

| RISK REGISTER |  |  |  |  |  |  | Version: Bid |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Name: West of England Combined Authority Traffic Signal Enhancement Works |  |  |  |  |  |  | Project Name: Programme Level |  |  |  |  |  |
| Risk Identifier: 009 |  |  | Risk Description: Lack of stakeholder support |  |  |  |  |  |  |  | Risk Category: Project |  |
| Probability: |  |  |  | Impact: |  |  |  | Expected Value: |  |  | Proximity: Delivery |  |
| Pre-Response 4 | Post-Response 2 |  |  | Pre-Response 5 | Post-Response 5 |  |  | Pre-Response 20 |  | Post-Response 10 |  |  |
| Risk Response Category: - Reduce the chance of the threat occurring or reduce impact of threat should it occur |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Response: There is Political support for the programme. A communication plan will be agreed and stakeholder engaged regarding the detail of the scheme which can be used to inform detailed design. |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Registered: 26th June 2017 |  | Risk Author: Gary Peacock |  |  |  | Risk Owner: Richard Lewis Project Manager |  |  | Risk Actionee: Project Manager |  |  | Risk Status: Active |
| RISK REGISTER |  |  |  |  |  |  | Version: Bid |  |  |  |  |  |
| Programme Name: West of England Combined Authority Traffic Signal Enhancement Works |  |  |  |  |  |  | Project Name: Programme Level |  |  |  |  |  |
| Risk Identifier: 010 |  |  | Risk Description: Loss of key personnel |  |  |  |  |  |  |  | Risk Category: Project |  |
| Probability: |  |  |  | Impact: |  |  |  | Expected Value: |  |  | Proximity: Delivery |  |
| Pre-Response 5 | Post-Response 2 |  |  | Pre-Response 5 | Post-Response 5 |  |  | Pre-Response 25 |  | Post-Response 10 |  |  |
| Risk Response Category: - Reduce the chance of the threat occurring or reduce impact of threat should it occur |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk Response: The makeup of the Project Board has been agreed there will be Senior Management Staff from each Council and suppliers with key skills. This will provide staff resilients as the programme is not reliant on one key member of staff. |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Registered: 26th June 2017 |  | Risk Author: Gary Peacock |  |  |  | Risk Owner: Richard Lewis Project Manager |  |  | Risk Actionee: Project Manager |  |  | Risk Status: Active |